## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2221-swen-261-06-maple-leafs
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a product user, I want to be able to login to a specified user account so I can do user specific stuff | GIVEN I try to login WHEN the username matches THEN I will be logged in
GIVEN I try to login WHEN the username doesn't match THEN the webpage will say the account doesn't exist
As a user I want to look up specific jerseys so I can find the jersey I want to buy | GIVEN I am at the search bar WHEN I enter a name THEN the website will show every jersey that has that name in it
GIVEN I am at the search bar WHEN nothing is entered THEN the website will show every jersey in the inventory
GIVEN I am at the search bar WHEN I enter a name that doesn't relate to any jersey THEN the website will display that no products were found
As an Admin, I want to see the specified information of a jersey, so I understand the product that I am interested in | GIVEN I am at the search bar WHEN I click on a jersey THEN I will be sent to the individual jersey's page (include player name, player number, cost, size dropdown menu, home/away, ID number), with buttons to go back, update, and delete
GIVEN I am viewing a jersey's page WHEN I click the back button THEN I will go back to the search bar
GIVEN I am viewing a jersey's page WHEN I want a jersey in a specific size THEN I will be able to select that size
As a buyer, I want to see the specified information of a jersey, so I understand the product that I am interested in | GIVEN I am at the search bar WHEN I click on a jersey THEN I will be sent to the individual jersey's page (include player name, player number, cost, size dropdown menu, home/away, ID number), with buttons to go back and add to cart
GIVEN I am viewing a jersey's page WHEN I click the back button THEN I will go back to the search bar
GIVEN I am viewing a jersey's page WHEN I want a jersey in a specific size THEN I will be able to select that size
As an Admin I want to remove jerseys so that customers won't see jerseys that are no longer available. | GIVEN The Admin is viewing a specific jersey WHEN the "delete jersey" button is clicked THEN a confirmation alert is shown
GIVEN the Admin clicked the "delete" jersey button WHEN confirm is clicked in the confirmation alert THEN the page will display a Jersey Not Found page
GIVEN a jersey has been deleted WHEN the admin goes back to the browsing products page THEN the deleted jersey should not be displayed
As an Admin I want to add jerseys so that I can show my customers what is available to buy. | GIVEN The Admin is viewing the available jerseys WHEN the "create jersey" button is clicked THEN a new page is displayed with fields to input a new jersey
GIVEN the Admin has the fields filled out and clicks the "add jersey" button WHEN there is no existing jersey with the same content THEN the new jersey should be created
GIVEN a jersey has been created WHEN the admin goes back to the browsing products page THEN the created jersey should be displayed
As an Admin I want to edit jerseys so that I can update my customers what is available to buy. | GIVEN The Admin is viewing a specific jersey WHEN the "update jersey" button is clicked THEN a new page with fields to edit the jersey is displayed
GIVEN the Admin has the edit fields filled out WHEN the "update jersey" button is clicked THEN the specified jersey should be changed and displayed
GIVEN a jersey has been edited WHEN the admin goes back to the browsing products page THEN the edited jersey should display the updated values
As a user I want the shopping cart to display jerseys so that I know what I am buying | GIVEN a customer has a non-empty shopping cart WHEN they click to show the shopping cart THEN I expect to see all jerseys that were added to the cart
GIVEN a customer has an empty shopping cart WHEN they click to show the shopping cart THEN I expect to see an empty cart page
As a buyer I want to add and remove products from my shopping cart so I can determine what I will buy and won't buy | Given I am logged in, when I click the "add to cart" button then the item will be added to my shopping cart and shows a message that it has been added
Given I am logged in, when I click the remove item button then the item will be deleted from my shopping cart
As a buyer I want to have my shopping cart save even when I log out so I can remember what I wanted to buy when I come back | Given I have items in my shopping cart when I log out then the items in my shopping cart will be saved to my account
Given I had items in my shopping cart when I log in then the items that were previously in my shopping cart will still be there
As an admin, I want my users and myself to find the website visually appealing so that it will be easier to navigate the site. | Given I am browsing the website when I navigate pages then I will find that it is visually appealing.
As a User I want to see the cost of all my items in my shopping cart so that I can see how much money I am about to spend. | Given I am a user when I go to the shopping cart page then I will see the total cost of my cart.
As an admin, I want to be able to put discounts/sales on certain items, so I can entice people to buy products. | Given I am logged in when I see the list of jerseys on the home page then jerseys will be shown along with the discount they have (if discount is greater than 0).
Given I am logged in when I view an individual jersey's page that has a discount greater than 0 then that jersey will be shown with the discount.
Given I am logged in as a user when I see the list of jerseys in my shopping cart then jerseys will be shown along with the discount they have (if greater than 0).
Given I am logged in as a user when I see the list of jerseys in my shopping cart then the total price will be correctly calculated and shown using any discounted prices.
Given I am logged in as an admin when I create a new jersey then the jersey will have a field for discount.
Given I am logged in as an admin when I edit a new jersey then the jersey will have a field for discount.
Given I am logged in as an admin when I create a new jersey with a discount out of the range of 0 to 100 then an error message will be displayed
Given I am logged in as an admin when I edit a new jersey with a discount out of the range of 0 to 100 then an error message will be displayed